## Tasks
Level | Id | Description | Cost | Effort | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TOP | 100 | Phase 1: Progress & Requirements Analysis | 9 | 8 | bar: 1 to 3
| 101 | Reading and pronunciation comprehension | 2 | 2 | bar: 1
| 102 | Creating a Gannt chart for team coordination | 1 | 1 | bar: 2
| 103 | Color Method/Parrot | 3 | 3 | bar: 2 to 3
| 104 | Parrot Merge – Code | 3 | 2 | bar: 3
TOP | 200 | Phase 2: Class Design | 15 | 9 | bar: 3 to 4
| 201 | Hardware Coordination so far | 5 | 3 | bar: 3
| 202 | Draft UML Diagram – Flowchart | 3 | 2 | bar: 3 to 4
| 203 | Final UML | 7 | 4 | bar: 4
TOP | 300 | Phase 3: Implementation – Verification | 18 | 16 | bar: 4 to 6
| 301 | Code task management | 6 | 3 | bar: 4
| 302 | Code Creation | 7 | 8 | bar: 4 to 6
| 303 | Test Cases | 5 | 5 | bar: 4 to 6
TOP | 400 | Phase 4: Final Verification | 13 | 12 | bar: 6 to 8
| 401 | Final Code Implementation (Merge Code) | 8 | 7 | bar: 6
| 402 | Final Code Verification (Debugging) | 5 | 5 | bar: 6 to 8
TOP | 500 | Phase 5: Reporting | 14 | 11 | bar: 1 to 9
| 501 | Creating a Temporary Report | 3 | 2 | bar: 1 to 9
| 502 | Creating a Final Report | 4 | 4 | bar: 8 to 9
| 503 | Checking a Final Report | 7 | 5 | bar: 9
TOP | 600 | Phase 6: Final Phase | 3 | 11 | bar: 9 to 10
| 601 | Preparing the code in the desired format – Delivery | 3 | 1 | bar: 9
| 602 | Beers | 0 | 10 | bar: 9 to 10

## File too
Level | Id | Description | Cost | Effort | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TOP | 100 | Phase 1: Progress & Requirements Analysis | 9 | 8 | bar: 1 to 3
| 101 | Reading and pronunciation comprehension | 2 | 2 | bar: 1
| 102 | Creating a Gannt chart for team coordination | 1 | 1 | bar: 2
| 103 | Color Method/Parrot | 3 | 3 | bar: 2 to 3
| 104 | Parrot Merge – Code | 3 | 2 | bar: 3
TOP | 200 | Phase 2: Class Design | 15 | 9 | bar: 3 to 4
| 201 | Hardware Coordination so far | 5 | 3 | bar: 3
| 202 | Draft UML Diagram – Flowchart | 3 | 2 | bar: 3 to 4
| 203 | Final UML | 7 | 4 | bar: 4
TOP | 300 | Phase 3: Implementation – Verification | 18 | 16 | bar: 4 to 6
| 301 | Code task management | 6 | 3 | bar: 4
| 302 | Code Creation | 7 | 8 | bar: 4 to 6
| 303 | Test Cases | 5 | 5 | bar: 4 to 6
TOP | 400 | Phase 4: Final Verification | 13 | 12 | bar: 6 to 8
| 401 | Final Code Implementation (Merge Code) | 8 | 7 | bar: 6
| 402 | Final Code Verification (Debugging) | 5 | 5 | bar: 6 to 8
TOP | 500 | Phase 5: Reporting | 14 | 11
| 501 | Creating a Temporary Report | 3 | 2
| 502 | Creating a Final Report | 4 | 4 | bar: 8 to 9
| 503 | Checking a Final Report | 7 | 5 | bar: 9
TOP | 600 | Phase 6: Final Phase | 3 | 11 | bar: 9 to 10
| 601 | Preparing the code in the desired format – Delivery | 3 | 1 | bar: 9
| 602 | Beers | 0 | 10 | bar: 9 to 10