## Personal Gant
100 | Phase 1: Progress & Requirements Analysis | 0
101 | Reading and pronunciation comprehension | 100 | 1 | 1 | 2 | 2
102 | Creating a Gannt chart for team coordination | 100 | 2 | 2 | 1 | 1
103 | Color Method/Parrot | 100 | 2 | 3 | 3 | 3
104 | Parrot Merge – Code | 100 | 3 | 3 | 3 | 2
200 | Phase 2: Class Design | 0
201 | Hardware Coordination so far | 200 | 3 | 3 | 5 | 3
202 | Draft UML Diagram – Flowchart | 200 | 3 | 4 | 3 | 2
203 | Final UML | 200 | 4 | 4 | 7 | 4
300 | Phase 3: Implementation – Verification | 0
301 | Code task management | 300 | 4 | 4 | 6 | 3
302 | Code Creation | 300 | 4 | 6 | 7 | 8
303 | Test Cases | 300 | 4 | 6 | 5 | 5
400 | Phase 4: Final Verification | 0
401 | Final Code Implementation (Merge Code) | 400 | 6 | 6 | 8 | 7
402 | Final Code Verification (Debugging) | 400 | 6 | 8 | 5 | 5
500 | Phase 5: Reporting | 0
501 | Creating a Temporary Report | 500 | 1 | 9 | 3 | 2
502 | Creating a Final Report | 500 | 8 | 9 | 4 | 4
503 | Checking a Final Report | 500 | 9 | 9 | 7 | 5
600 | Phase 6: Final Phase | 0
601 | Preparing the code in the desired format – Delivery | 600 | 9 | 9 | 3 | 1
602 | Beers | 600 | 9 | 10 | 0 | 10